## Full Report
Decentralized Capital Budget Programme - 2018- .puttlam District | [22 empty] | Annexure No.1
Physical and Financial Progress of the Month of November - 2018
Divisional Secretariat Division (a) |  | Name: Mahakumbukkadawaa
No: 1182
SN | Name of MP | Name of Project | අංශය | G.N. Division (b) |  | Sector | Type of Project (Construction / Goods & Services) | Total Estimate Cost (Rs.) |  | Allocation (Rs.) | Expenditure (Rs.) | Unit of Measure | Physical Progress (c) | [9 empty] | No of Beneficiaries | Remarks
|  |  |  | Name | No |  |  | With VAT | Without VAT |  |  |  | A | B |  |  |  | C | D | E | F | G
[14 empty] | B1 | B2 | B3 | B4
1 | Priyankara jayarathna | Providing Buffe Set for Peramaga Sathkara Societes Kiula youth Project. |  | Kiwula Youth Project | 10377 | SW | Goods |  |  | 40000 | 40000 | [10 empty] | √ | 45
2 |  | Construction of fens in udamaluwa for Welasiys iyanayaka Dewalaya. |  | Kiwula Youth Project | 10377 | SW | Goods |  | 202411.8 | 200000 |  |  |  | √ | [8 empty] | 25
3 |  | Finishing the rest work of mailawawa Community Hall Building. |  | Mohoriya | 10398 | SW | Construction |  | 221672.59 | 200000 | 187427.06 | [10 empty] | √ | 105
4 |  | Surfacing wall work to buthigama Community hall |  | Adigama |  | SW | Construction |  |  | 100000 |  |  |  | √ | [8 empty] | 110
5 |  | build-up the basement to extend the surakkulama community hall |  | Grayaggama | 10390 | SW | Construction |  |  | 300000 |  |  |  | √ | [8 empty] | 82
6 | Ashoka Priyantha | Electricity supply Community hall. |  | mohoriya | 10392 | RE | Services |  |  | 20000 | 19400 | [10 empty] | √ | 41
7 |  | Thapal linda Water Tank Power Supply. |  | kiula 04 -02 | 10375 | RE | Services |  |  | 20000 | 19400 | [10 empty] | √ | 82
8 |  | G.S Residency Electricity supply. |  | kiula 04 -01 | 10376 | RE | Services |  |  | 20000 |  |  |  | √ | [8 empty] | 63
9 |  | Providing equipment for rejistered socity Mahakumbukkadawala Division. |  |  |  | SW | Goods |  |  | 200000 |  |  |  | √ | [8 empty] | 205
10 |  | Providing equipment for rejistered free school Mahakumbukkadawala Division. |  |  |  | SW | Goods |  |  | 100000 |  |  |  | √ | [8 empty] | 110
11 | Priyankara jayarathna | Providing equipment for kiula Commiunity hall. |  | kiula 04 -01 | 10376 | SW | Goods |  |  | 100000 | 100000 | [10 empty] | √ | 135
12 |  | finishing the roof work dimuthu free school -kiula 04 -2 |  | kiula 04 -02 | 10375 | SW | Construction |  |  | 200000 |  |  | √ | [9 empty] | 0
13 | Niroshan Perera. | Providing Chairs for agree socity . | Providing Chairs for agree socity . | mohoriya | 10392 | SW | Goods |  |  | 40000 | 40000 | [10 empty] | √ | 42
14 |  | Providing equipment for rejistered Society Mahakumbukkadawala Division. |  |  |  | SW | Goods |  |  | 75000 |  |  | √ | [9 empty] | 132
15 | Sanath nishantha. | 75M paddy feild water way making at 613E dangaswewa sohamankulama |  | Dangaswewa. | 10381 | MI | Construction |  |  | 200000 | 194000 |  |  | √ | [8 empty] | 48
16 | Priyankara jayarathna | Purchasing building material for build-up the building of kivula 04 united funeral society |  | kiula 04 -01 | 10376 | SW | Goods |  |  | 100000 | [12 empty] | 285
17 | Palitha Range Bandara | B Galkuliya church surrounding area filled and bulidup with boral meteril. |  | w.Galkuliya |  | RA | Construction |  | 194013 | 200000 |  |  | √ | [9 empty] | 98
18 |  | Providing equipment to for rejistered socity in Mahakumbukkadawala Divigsion |  |  |  | SW | Goods |  |  | 100000 | 99190 | [10 empty] | √ | 210
19 |  | Building meterial providing byparents to Barankattuva School. |  | Barannankattuwa |  | SW | Goods |  |  | 200000 |  |  | √ | [9 empty] | 450
20 |  | A VIP hut providing by kivula youth associate to udhaya maranadhara socirty. |  | Kiwula Youth Project | 10377 | SW | Goods |  |  | 50000 |  |  |  | √ | [8 empty] | 135
21 |  | Road repairing from J.M.Nimal Dayarathna residence to kawayankulam. |  | Kawayankulama |  | RA | Construction |  | 194102.91 | 200000 |  |  | √ | [9 empty] | 53
22 | Arundika pranandu | Pending works of common hall at Sarwodaya village of kandayaya GN division |  | kiula 04 -02 | 10375 | SW | Construction |  | 223382.37 | 200000 |  |  | √ | [9 empty] | 75
23 |  | cultural hall works at walpaluwa primery school. |  | Walpaluwa |  | SW | Construction |  |  | 200000 |  |  | √ | [9 empty] | 310
24 | Hector appuhami | setup toilet work for baranankattuwa junior school | Barannankattuwa. | Barannankattuwa |  | SW | Goods |  |  | 200000 |  |  | √ | [9 empty] | 450
Total | [8 empty] | 1035582.67 | 3265000 | 699417.06 | [11 empty] | 3291
(a) - Please see the Annexure No.3 for Divisional Secretariate Divisions Names & Nos.
0
(c ) - Instructions to fill the Physical Progress
| Description for rating |  |  |  | Rates | Percentage Ranges
| Estimate is being / to be prepared and initial works started |  |  |  | A | (0 - 5)%
| Constructions: B - 1 = Estimates approved / Bid documents prepared, B - 2 = Quotation / Bid called B - 3 = Quotation / Bid Received B - 4 = Contract Awarded. (25% completed) Other : Identified Institutions / CBO's to provide Goods/ Instruments Obtain required list of goods, Estimated prepared |  |  |  | B | (6 - 25)%
| Constructions : Started construction works , (40% completed) Other : Placed orders for goods / instruments |  |  |  | C | (26 - 40)%
| Constructions : 60% Completed Other : Received goods / instruments as per the order |  |  |  | D | (41 - 60)%
| Constructions : 80% Completed Other : Received goods / instruments as per the order |  |  |  | E | (61 - 80)%
| Constructions : 99% Completed Other : Completed lists of goods to be given to beneficiaries |  |  |  | F | (81 - 99)%
| Constructions : 100% Completed Other : Issued goods and instruments to identified institutions/ CBOs |  |  |  | G | 100%